## Task Board
[5 empty] | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item |  | Task | Task Owner |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27
|  |  |  | Initial Estimate (Total Sprint Hours = 40 x 5) | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03
|  |  |  | Ideal Burndown | 200 | 190 | 180 | 170 | 160 | 150 | 140 | 130 | 120 | 110 | 100 | 90 | 80 | 70 | 60 | 50 | 40 | 30 | 28 | 26 | 24 | 22 | 20 | 16 | 12 | 8 | 5 | Ideal Burndown
| User Story Id |  |  | Remaining Hours | 200 | 187 | 171.5 | 163.5 | 155.5 | 147 | 138 | 125 | 117.5 | 107.5 | 74.5 | 80 | 61 | 46.5 | 37 | 32 | 22 | 12.5 | 7 | 8 | 4.5 | 0.5 | 5 | 5 | 3 | 0 | 2.5 | Remaining Hrs (Total)
Research and Design Phase | Spike: Understanding the technical challenges and all research needed to do a successful completion of Victory Warriors game | Game discussion and selection | All | 0 | 2019-04-08: 0.5; 2019-04-10: 0.5
|  | Game Ideas Selection | All | 0 | 2019-04-09: 0.5; 2019-04-14: 0.5; 2019-04-16: 0.5
|  | XP value selection for each member | All | 0 | bar: 2019-04-08
|  | Initial setup of readme.md | Karthika | 0 | 2019-04-08: 0.5; 2019-04-09: 1; 2019-04-13: 0.5
|  | Greenfoot PoC for actors movement | All | 0 | bar: 2019-04-09 to 2019-04-12
|  | UI Wireframes | All | 0
|  | Greenfoot to droidfoot Mobile PoC | Priya K | 0 | 2019-04-13: 0.5; 2019-04-15: 1; 2019-04-16: 1; 2019-04-17: 1; 2019-04-19: 1
|  | Game sound and image selection | Karthika | 0 | 2019-04-10: 1; 2019-04-11: 0.5; 2019-04-14: 1; 2019-04-16: 0.5
|  | Setup and maintain scrum board on Google Drive | SaiPrithipa | 0 | bar: 2019-04-09; 2019-04-17; 2019-04-22; 2019-04-29
|  | GIT setup | All | 0 | bar: 2019-04-08 to 2019-04-11
|  | Maintain Project journal | All | 0 | 2019-04-11: 2; 2019-04-12: 2
|  | Use Case Story Spcecification | SaiPrithipa | 0 | 2019-04-09: 2; 2019-04-13: 1; 2019-04-14: 1
|  | Add rules to the Game | All | 0 | 2019-04-09: 2; 2019-04-10: 3
|  | Integrate design pattern | All | 0 | 2019-04-15: 0.5; 2019-04-25: 0.5; 2019-04-27: 1; 2019-04-29: 1
Development Phase | 2-Displaying the player component in the game screen | Animating a player icon with unity asset (Includes learning how to play around and use unity.) | SaiPrithipa | 0 | 2019-04-17: 3; 2019-04-18: 1; 2019-04-19: 1; 2019-04-20: 2; 2019-04-21: 1; 2019-04-22: 1
|  | Display player in the screen | SaiPrithipa | 0 | 2019-04-17: 3; 2019-04-18: 1; 2019-04-19: 2; 2019-04-20: 1; 2019-04-21: 1; 2019-04-22: 1
|  | Display player with property in the screen | SaiPrithipa | 0 | bar: 2019-04-18; 2019-04-20
|  | Player movements in the screen. | SaiPrithipa | 0 | 2019-04-17: 1; 2019-04-19: 1; 2019-04-20: 2; 2019-04-21: 1; 2019-04-24: 1
|  | To make the player jump | SaiPrithipa | 0 | bar: 2019-04-22 to 2019-04-23
|  | To make the player cross their hurdles | SaiPrithipa | 0 | 2019-04-23: 1; 2019-04-24: 2; 2019-04-25: 1; 2019-04-27: 1; 2019-04-30: 1
|  | Player's label on the screen | SaiPrithipa | 0 | bar: 2019-04-28; 2019-05-03
|  | Player attacks (Integrate with opponent component) | SaiPrithipa | 0 | 2019-04-20: 1; 2019-04-21: 2; 2019-04-23: 1; 2019-04-24: 1; 2019-04-25: 2; 2019-04-26: 2; 2019-04-27: 2
|  | Player need to make use of lucky powers (Integrate with lucky power component | SaiPrithipa | 0 | bar: 2019-04-22; 2019-04-25 to 2019-04-29
|  | Player hits/wins should reflect in the score box(Integrate with score component) | SaiPrithipa | 0 | bar: 2019-04-17; 2019-04-20; 2019-04-24 to 2019-04-25; 2019-04-28 to 2019-04-29
|  | Player need to make use of properties to cross hurdles (Implemented jump and right as a new requirement change.) | SaiPrithipa | 0 | bar: 2019-04-21; 2019-04-23; 2019-04-25; 2019-04-27
|  | Player needs to be defeated | SaiPrithipa | 0 | bar: 2019-04-26; 2019-04-28
|  | Player needs to win | SaiPrithipa | 0 | bar: 2019-04-22; 2019-04-25; 2019-04-27; 2019-04-30 to 2019-05-01
|  | Integrate with treasure component (logic for treasure show) | SaiPrithipa | 0 | 2019-04-28: 2; 2019-04-29: 1; 2019-04-30: 1; 2019-05-01: 1
| 14- Adding sound for the player component | Select sounds that are suitable for the player component | SaiPrithipa | 0 | bar: 2019-04-20; 2019-04-22; 2019-04-25
|  | Add sounds for player movements (walk) | SaiPrithipa | 0 | 2019-04-27: 2
|  | Add sounds for player movements (jump) | SaiPrithipa | 0 | 2019-04-27: 0.5
|  | Add sounds for player attacks (hit enemy) | SaiPrithipa | 0 | bar: 2019-04-27 to 2019-04-28
|  | Add sounds for player attacks (getting hit) | SaiPrithipa | 0 | bar: 2019-04-27 to 2019-04-28
|  | Add sounds for decrease in healthbar | SaiPrithipa | 0 | 2019-04-28: 2
|  | Implement a good design using pattern to integrate sound and player | SaiPrithipa | 0 | 2019-04-29: 1; 2019-04-30: 2
| 5-Displaying the lifeline component in the game screen | Player should have a lifeline displayed on the screen | SaiPrithipa | 0 | 2019-04-19: 2; 2019-04-25: 1; 2019-05-01: 1
|  | Player losing hits should reflect in his lifeline status | SaiPrithipa | 0 | 2019-04-23: 2; 2019-04-24: 2; 2019-04-26: 1; 2019-04-29: 2; 2019-04-30: 1
|  | Lifeline should decrease if player gets hit by an opponent | SaiPrithipa | 0 | bar: 2019-04-26 to 2019-04-28
|  | Lifeline should increase if player touches a specific lucky power (Integrate with lucky power component) | SaiPrithipa | 0 | bar: 2019-04-27 to 2019-04-28; 2019-05-01
|  | Increase/Decrease in lifeline should reflect in the game screen | SaiPrithipa | 0 | bar: 2019-04-22; 2019-04-26; 2019-04-30
| 6-Displaying the treasure component in the game screen at the completion of level 1. | The treasure should be displayed in the screen after the player completes a level. | Priya Khadke | 0 | 2019-04-14: 0.5; 2019-04-19: 0.5; 2019-04-20: 1; 2019-04-21: 1
|  | The player should be able to take the treasure. | Priya Khadke | 0 | 2019-04-18: 0.5; 2019-04-23: 1; 2019-04-24: 1
|  | Message like “level completed” should be displayed. | Priya Khadke | 0 | 2019-04-22: 0.5; 2019-04-24: 0.5; 2019-04-28: 0.5
| 7-Displaying the lucky power components in the game screen | The player should be able to see the powers while playing. | Priya Khadke | 0 | 2019-04-25: 0.5; 2019-04-26: 1; 2019-04-28: 1
|  | The player should be able to move near the powers and touch them. | Priya Khadke | 0 | bar: 2019-04-20; 2019-04-22; 2019-05-03
|  | Once the player touches the power, the player should gain more points and the same should be added to the score | Priya Khadke | 0 | bar: 2019-04-17 to 2019-04-19; 2019-04-26
|  | The score should be updated accordingly. | Priya Khadke | 0 | bar: 2019-04-28 to 2019-04-30; 2019-05-02
|  | The player should gain one extra lifeline after touching the lucky charm power.(call player component only) | Priya Khadke | 0 | 2019-04-27: 0.5
| -Displaying the negative power components in the game screen (implemented for component only later made out of scope) | The player should be able to see the negative powers while playing. | Priya Khadke | 0 | bar: 2019-04-23
|  | The player should be able to move near the negative powers and touch them. | Priya Khadke | 0 | bar: 2019-04-27 to 2019-04-28
|  | Once the player touches the negative power, the player should loose points and the same should be added to the score | Priya Khadke | 0 | bar: 2019-04-20 to 2019-04-22
|  | The score should be updated accordingly. | Priya Khadke | 0 | bar: 2019-04-17 to 2019-04-19; 2019-04-23
| -Displaying the lucky charm components in the game screen | The player should be able to see the lucky charm while playing. | Priya Khadke | 0 | bar: 2019-04-17; 2019-04-19 to 2019-04-20; 2019-04-25
|  | The player should be able to move near the lucky charm and touch them. | Priya Khadke | 0 | bar: 2019-04-17; 2019-04-21; 2019-04-24; 2019-04-26
[15 empty] | 1 |  |  |  | 1 | 1 | 1
| 8-As a player, I should be able to get a great user experience with the background component of the game screen. | Searching best suiting images for background | Karthika Arumugam | 0 | 2019-04-14: 0.5; 2019-04-21: 1; 2019-04-28: 1
|  | Make Background appears clearly through out the game | Karthika Arumugam | 0 | bar: 2019-04-17 to 2019-04-19; 2019-04-23
|  | Background should be displayed throughout the game until the game ends. | Karthika Arumugam | 0 | bar: 2019-04-17; 2019-04-19 to 2019-04-20; 2019-04-25
|  | background should make use of dynamically changing components | Karthika Arumugam | 0 | bar: 2019-04-17; 2019-04-21; 2019-04-24; 2019-04-26
|  | background should make use of multiple objects. | Karthika Arumugam | 0 | bar: 2019-04-17; 2019-04-21 to 2019-04-23
|  | background should match the sound effects. | Karthika Arumugam | 0 | bar: 2019-04-25 to 2019-04-26
| 9-As a player, I should be able to play the game with sound effects and music played throughout the game | The music should be played throughout the game until the level 1 is completed. | Karthika Arumugam | 0 | bar: 2019-04-23 to 2019-04-24; 2019-04-26
|  | The music should be played throughout the game until the player gets defeated. | Karthika Arumugam | 0 | bar: 2019-04-21; 2019-04-24
|  | The music should be accompanied by sound effects. | Karthika Arumugam | 0 | bar: 2019-04-23; 2019-04-25 to 2019-04-26
|  | A sound should be played when the player loses a lifeline. | Karthika Arumugam | 0 | bar: 2019-04-20 to 2019-04-21; 2019-04-24
|  | A sound should be played when the player touches the positive powers. | Karthika Arumugam | 0 | bar: 2019-04-25
|  | A different type of sound (distinguish from other sounds) should be played when the user completes a level. | Karthika Arumugam | 0 | 2019-04-24: 0; 2019-04-28: 1; 2019-05-01: 1
|  | A sound should be played when the user takes the treasure. | Karthika Arumugam | 0 | bar: 2019-04-29; 2019-05-02
| 3-Displaying enemies/hurdles component in the screen. | Display multiple hurdles/enemies in the screen | Priya Yadav | 0 | bar: 2019-04-17 to 2019-04-19; 2019-04-21; 2019-05-01
|  | Searching best suiting images for Enemy walk | Priya Yadav | 0 | bar: 2019-04-19 to 2019-04-20; 2019-04-22; 2019-04-24
|  | Searching best suiting images for Enemy attack | Priya Yadav | 0 | bar: 2019-04-17; 2019-04-23; 2019-04-26; 2019-04-29
|  | Searching best suiting sound for Enemy attack | Priya Yadav | 0 | bar: 2019-04-18; 2019-04-24; 2019-04-28; 2019-05-02
|  | Searching best suiting sound for Enemy Die | Priya Yadav | 0 | 2019-04-15: 1; 2019-04-17: 1; 2019-04-18: 1; 2019-04-20: 2; 2019-04-21: 1
|  | Display enemies with property in the screen | Priya Yadav | 0
|  | Display negative powers | Priya Yadav | 0 | bar: 2019-04-17; 2019-04-19; 2019-04-21 to 2019-04-22
|  | Display enemy movements/hurdles movements in the screen. | Priya Yadav | 0 | bar: 2019-04-23 to 2019-04-27
|  | Negative powers should appear suddenlty. | Priya Yadav | 0 | 2019-04-20: 2; 2019-04-25: 2; 2019-04-29: 1; 2019-04-30: 1; 2019-05-01: 1; 2019-05-02: 1
|  | Enemies shoud attack on to the Player | Priya Yadav | 0 | 2019-04-17: 1; 2019-04-18: 0.5; 2019-04-19: 1; 2019-04-20: 1; 2019-04-22: 1; 2019-04-27: 0.5
|  | Enemies attacks (Integrate with player component) | Priya Yadav | 0
|  | Enemies needs to be defeated | Priya Yadav | 0 | bar: 2019-04-24 to 2019-04-27
|  | Enemies need to cloned to be spawned | Priya Yadav | 0 | 2019-04-21: 2; 2019-04-25: 1; 2019-04-29: 2; 2019-05-01: 1
|  | Enemies needs to win | Priya Yadav | 0 | 2019-04-19: 2; 2019-04-20: 1; 2019-04-21: 1; 2019-04-22: 1; 2019-04-23: 1; 2019-04-28: 2
| 1-Displaying the score board component in the screen | The score should be displayed in a box. | Anushree Menon | 0 | 2019-04-14: 0.5; 2019-04-16: 0.5; 2019-04-21: 1
|  | The score should be updated (increased or reduced) depending on the attacks. | Anushree Menon | 0 | bar: 2019-04-14; 2019-04-17; 2019-04-20
|  | The score should be stored in some form and should be carried forward to the next levels. | Anushree Menon | 0 | 2019-04-17: 0.5; 2019-04-19: 0.5; 2019-05-03: 0.5
|  | The score should start from 0 and the UI should display the score clearly. | Anushree Menon | 0 | 2019-04-20: 0.5; 2019-04-22: 0.5
|  | The score should reduce when coming in contact with negative powers | Anushree Menon | 0
| 4-Completing the level 1 of the game | The player should be able to complete the level 1. | Anushree Menon | 0 | bar: 2019-04-21 to 2019-04-22
|  | The player should complete the level 1 after killing all the enemies and passing all the hurdles. | Anushree Menon | 0 | bar: 2019-04-23; 2019-04-27
|  | The player should be able to reach the end of the level 1. | Anushree Menon | 0 | bar: 2019-04-25
|  | The player should not be able to complete the level if he/she loses. | Anushree Menon | 0 | bar: 2019-04-26 to 2019-04-27
|  | Class Diagram | All | 0 | 2019-04-28: 1; 2019-04-29: 1; 2019-04-30: 1; 2019-05-02: 4
|  | Use Case diagram | Karthika | 0 | bar: 2019-04-30 to 2019-05-01
|  | Activity Diagram | Priya Y | 0 | bar: 2019-04-30 to 2019-05-01
|  | Sequence Diagram | Sai Prithipa | 0 | 2019-05-01: 2; 2019-05-02: 2; 2019-05-03: 1
Testing |  | Integration Testing and Bug fixes | All | 0 | 2019-04-27: 1; 2019-04-28: 3; 2019-04-29: 2; 2019-04-30: 1; 2019-05-01: 2; 2019-05-02: 5; 2019-05-03: 1
Project Demo |  | Making of ad video for the game | Sai Prithipa | 0 | 2019-04-30: 2; 2019-05-01: 1; 2019-05-02: 4; 2019-05-03: 2
|  | Youtube game promo video | All | 0 | 2019-04-30: 2; 2019-05-01: 1; 2019-05-02: 1; 2019-05-03: 2
|  | Demo Presentation Deck | All | 0 | bar: 2019-04-30 to 2019-05-03
Karthika |  | 10 hours / Week
Sai |  | 10 hours / Week
Anushree |  | 10 hours / Week
Priya Y |  | 10 hours / Week
Priya K |  | 10 hours / Week
Total Available Hours During Sprint: |  | 200